## Sheet1
Sr. No | Areas | Details | Development
1 | Common elements of platforms to be enabled :
| a) Audit Trail Report | This is framework specific report which just needs to be called out from system. | Done
| b) Delegate Responsibility | This is a framework specific functionality for the user in user panel | Done
| c) Linking Accounts | This is a framework specific functionality for the user in user panel | Done
| d) User Management (Upgrading our existing user management to align it with framework components) | Convert our existing "Tenant" Users into the Users Management Format | Done
2 | Appearance Settings ( For logo and Name of Solution) in lines of Compliance hub. | This is in lines of "Compliance Hub" where we want a logo and Name of the solution to be customised for user. | Partially Done
3 | Compliance Certificate (for contractors) | In lines of Compliance Certificate as illustrated in Compliance Hub where user will have option to : Generate and View Certificate and Customize Language
4 | Dashboard logics and their redirection,
5 | Helpdesk in lines of Compliance Hub | An email id will be created and the user will be redirected to "Send mail" with an email id and Subject line. | Partially Done
6 | Notification Bell in lines of Compliance Hub | Notification bell to be enabled from framework on below events : 1. Records entered in modules for verification (where workflow templates enabled) 2. Records rejected by reviewer 3. Compliances due 4. License renewals due 5. Updates in Compliance Module
7 | Validation of PAN, Aadhar/ GST/ EPF / ESIC | API will be shared by KPMG
8 | Wage Register | - How will comp-off be added for working on NFH – Re-check Nirav to prepare format of Comp-off development and confirm to Promact team - We need Contractor's Name, Work order details in dashboard
9 | Exceptional report - Budget Vs Actual Deployment | We need Contractor's Name, Work order details in dashboard
10 | Payroll Continget workforce - Appointment letter & Experience letter | Option to generate appointment letter and experience letter
11 | In the work flow template, we need to add the toggle button to select approval required by Any / All added reviewers | This will enable all or any one to approve / reject the records

## Email
Entries in Module |  | Type | Required to Change
Reminder for approval, | Budget Module | Manual | Yes
Intimation of Approval, Rejection and Sent Back for correction | Contractor Registration | Manual | Yes
| Work-Order Database | Manual | Yes | Description - "Contractor is required to raise a claim at predefined interval through the portal and the concerned reviewer shall be required to validate the same considering the data available in system"
| Contingent Work-Force | Manual | Yes
| Advances | Manual | Yes
| Leave Management | Manual | Yes
| Fines / Penalties | Manual | Yes
| Construction Activity | Manual | Yes
| Reporting Accidents | Manual | Yes
| Contractor Invoice Claim | Manual | Yes
Monthly Reminders | Approve Monthly Attendance on Payroll Closure
Compliance Reminder | 2 days before due date
Compliance Intimation | Approval and Rejection of Compliance post review
Dual authentication | After login | System Generated | No
Password reset | After user created -- removed | System generated | No
Send Activation Mail | After user created -- removed | System generated | No
Forgot Password | On login page | System generated | No