## Email Body Observation (Sagar)
Points | Sagar's Remark | Remarks as per 25th Nov 20 | Remarks as per 26th Nov 20 & 27th Nov 20 | Remarks as per 30th Nov 20 | Status as on 7th Dec 20 | promacts remark 08/12/2020
Export to Excel functionality for All modules | Non-functional for module - 1) Health registers. 2) Contractor Claim | Kanan & team to work on this | ? | 1) Health Register - Columns like (Work Order Number, Gender) from report "Export to Excel" should be at start 2) Contractor Claim - Columns like (Department, Designation, Location, Employee Category) from report "Export to Excel" should be at start | 1) Done 2) Done
Export to Excel/Bulk upload - Apply permissions | Export functionality through (system role) is Functional. We also try giving access of Contractor Claim to all contractor logins but are unable to see the same in Contractor login | Kanan & team to check regarding number of module to be on a same page | ? | Done. Have cross checked by giving permission for module " Tax dedcuted at source" for Ankur's Contractor login | Already Done
Bulk Upload functionality | Done | Already Done | Already Done | Already Done | Already Done
Exceptional Reports | 1) We need "Date Filtration" functionality for exceptional reports like - Contractors license expiries, Actual Deployment Exceeds Sanctioned Strength, Child labor reports,Minimum wage non compliances, Contractor duplicate bank account numbers, Contingent Workforce registered under multiple Contractors | 1)There should be a date range functionality in each exceptional report - “From date” & ”To date” | 1) Report 1 – will remain same (Single date) Report 2 – Double date (from date & to date) Report 3 – Single date Report 4 – Single date Report 5 – Month & year filter Report 6 – Single date Report 7 (Cont. workforce registered under multiple contractors):– Only Active data should be reflected. Also Promact team to do the required alterations regarding company statutory details duplication. Report 8 – All ok Report 9 – All ok | Testing inprogress | Testing inprogress | Testing inprogress
| 2) Report "Actual Deployment Exceeds Sanctioned Strength":- i) There should be alteration in format for this report. Have emailed you required changes. | 2)Kanan & team to make required changes against exceptional report “Actual Deployment Exceeds Sanctioned Strength”. Desired format has been mailed. | ? | Testing pending | Testing pending | Done
| Also Promact claims that this alteration will have an impact on other working | - | - | - | -
Email Template | Demo to be given by Kanan | 1)Kanan to change URL in all Email Templates | ? | Pending | Pending | Development inprogress
|  | 2)Functionality for editing text of Email templates within the tool. (Kanan to discuss with Ankit) | ? | Pending | Pending
Auto Approval – WFT | Done. We have checked regarding leave management | Toggle button in “Work flow template - Leave Management” to get activated in Phase 2 | ? | Tested - We cant see toggle button while editing WFT | Tested - We cant see toggle button while editing WFT | Will discuss in todays call.
Master - Work pay policy changes | Only be tested once the wage register is complete | Wage register & Payslip report have been completed & are ready for testing. Once these reports have been tested KPMG will do testing on “Work Pay Policy” |  |  | Pending from KPMG
Module - Leave Management - Flexible Leaves | Done | Already Done | Already Done | Already Done | Already Done
Reports changes | Wage register & Payslip & other changes which were required as per “Status & Feedback” sheet | Wage register & Payslip report have been completed & are ready for testing. |  |  | Pending from KPMG
Display data as per logged in User | Only user should see their own data. | Done. (Cross-checked through Cont. Workforce) | Already Done | Already Done | Already Done
Export to excel - this should be done based on logged in user wise | Export to excel should displays only data pertaining to logger | Done. (Cross checked though Contractor Registration) | Already Done | Already Done | Already Done
View option in modules | Done | Already Done | Already Done | Already Done | Already Done
Validation in Red for fields | Done | Already Done | Already Done | Already Done | Already Done
Exceptional Report - Report 4 - Child Labour Deployment - Do changes as below: | Done | Already Done | Already Done | Already Done | Already Done
Child Labours for < 14 years
Young Adults for 14 to 18 years
Contractor & Contingent Workforce Permission option | Done | Already Done | Already Done | Already Done | Already Done
Add Contractor Claim in WFT | Done | Already Done | Already Done | Already Done | Already Done
Remove tenant change option from Login and it should be from URL | Done | Already Done | Already Done | Already Done | Already Done
Holiday Master - There should be a bulk upload functionality to upload all the calender Holidays | Done | Already Done | Already Done | Already Done | Already Done
We would like to have a bulk upload functionality in Masters – Tenant User |  | New Requirement from KPMG |  | Testing pending | Done
Master - Location |  | System falsely displaying as - Location code already exist |  | Testing pending | Done
Module - Budgeting |  | Current head count not getting auto populated via Cont. Workforce while creating budget. Kanan to check with internal team & will be getting back to us |  | In progress | Done – We require a discussion for this point with you. Please let us know suitable time on Monday. | Done – We require a discussion for this point with you. Please let us know suitable time on Monday.
Module - Work Order Database |  | Small fluctuation in Start & end date. System tends to take a day before given Start or end date. For eg - End date mention = 23 Oct20. Than system will consider End date as 22 Oct20. Kanan & Team to re-check on this & also to cross check as to why particular fields appear as blank while doing editing |  | 1) Desired changes are reflecting on summary dashboard. However, the same changes are not getting reflected through the "View" option. It's still showing the concept of (-1 day) 2) In Progress | 1) Done. The desired changes are getting reflected on Dashboard as well as "View" Option 2) Not Done | 1. Done 2. Done
Module - Advance |  | 1) Advance recovered shouldn’t exceed wage payable (excel “Wage Registers Error” attached) | 26/11/2020 (Devashree):- After internal discussion we found that we will have to change the azure function or change implementation for advances repaid. So we are not changing payroll dates right now as implementation is going to change. We suggest you that part later. | 30/11/2020 (Krishna) - It is possible. but promact team have to confirm some points. Correct Payroll calculation will get refletced during month end. It will be on Net payable. & if any shortfall in amount it will get added in next month | In Progress | Done
|  | 2) We had applied for advance of INR 5k in name of work force named dhh on 02 May 20 to be recovered in 2 installment from May. Then we processed the wage register for May. But the amount outstanding in the advance module is still coming as INR 5K and total advance repaid is shown as 0. (Screen shot “Outstanding Amount & Unchanged Outstanding Amount” attached) |  | Inprogress | In Progress | Done
Module - Leave Management |  | 27/10/2020 (Sagar) - Designation field yet to be added | Promact Team - This will be done | Pending | Done
Module - Daily Attendance |  | 1) Future Date entry should not be allowed in Daily attendance | 1) To be done. Restriction should be from front end as well as from bulk upload. | Done. Have cross checked through front end as well as through Bulk upload functionality | Already Done
|  | 2) In the excel sheet downloaded using export to excel option OT hours , Intime, out time is not coming in proper format. For eg:- 19:0 | 2) This will be done (Formatting into double digits) | In progress | Done
|  | 3) Also we tried to insert "In Time" for Contingent workforce Sagar17 as 19.15 from front end. However, when we extracted the daily attendance in excel the "In Time" for the same records are reflecting as 19:0 (Daily Attendance Screenshot & Excel attached) | 3) No observations on this. | Already Done | Already Done
Module - Bonus Payment |  | Negative entry should not be allowed in Bonus module while editing the records | Promact Team - This will be done | Done. Have tested by saving negative entries | Already Done
Master - Holiday |  | I have mentioned 2 holidays in the month of Nov 20. However when I cross-checked the same in attendance register only 1 National holiday is getting reflected. Rest all ok. Also Holiday Master has been linked to Attendance Register | Promact Team - This will be done | Done. Have tested attendance register by adding 2 more holidays in Master- Holiday for the month of Nov20 | Already Done
Flexible Leave |  |  | 1) In Admin Login despite mentioning 0 leaves under “Flexible Leave” field in Tenant Details, system still allowing to grant such type of leaves. Promact team to work on internal controls of Flexible leave under Admin login. | ? | Need update | Done
|  |  | 2) Also in Module Leave management – Promact team will be adding 1 more option in leave type “Unpaid Leave”. Promact team to discuss internally & to give flexible solution on this | ? | Need update | Done
Cont. Work force |  |  | Email Id for worker to be made non mandatory | Promact team will check by making its non mandatory (Change Request) | Need update | We will discuss in todays call
Fine & Penalties |  |  | Need "Reason for fine" column | Promact team will add it (Change Request) | Done
Compliance Management |  |  | We need to provide docs upload option under comp. management | Already Done | Already Done
Master - Work Policy |  |  | Need to test for report generation with past date records. Need to check on creation of new policies. Also, what in case if we want to stop application of policy, how can we do that | Need Taufel to discuss. We will check it in 01/12/2020's status call | Need update | We will discuss in todays call
Creation of Exception report |  |  | We need exception report for cases where Work order is created without employer registration number. This can give us details of vendors not included under vendor list in Registration certificate | Nirav to share format of the new report. Emp Cont. registration ID field already there. Hence Exceptional report is no longer required | Done
Module Construction Activity |  |  | Need option to add line items in "Year Wise Construction Details" | to add 2 more years. Still Promact will confirm on this case. (Change Request) Promact team will check and let you inform. | Need update
Module - Reporting Accidents |  |  | To make reason for not giving first aid kit as mandatory in case First aid not ticked | To be done | Done
Module - Daily Attendance |  |  | Overtime / total work time not displayed under view | Pending | Done
Exception report - "Contingent Workforce registerd under multiple Contractors" |  |  | 1) We can also have exception based on PAN no 2) Also why is gender getting displayed as 1 or 0 in summary dashboard 3) We can also have a report showing workforce wise contractors which where registered | 1) To be done 2) To be done 3) Not needed | 1) Done 2) Done 3) Not Needed
Exception report - "Maximum permissible hours" |  |  | We can also have work order no./contractor name in report | To be done | Done
|  |  | TDS master creation & Auto calculation of TDS Amount - Next Phase release | Not needed (As discussed with Vivek) | Not Needed
Module - Health Register |  |  |  | While doing Bulk upload :- If "Suspended from work" has been ticked as "No" then excel should not ask for "Suspension Start date & End date" as required or mandatory field | 1) While doing Bulk upload :- If "Suspended from work" has been ticked as "No" then excel should not ask for "Suspension Start date & End date" as required or mandatory field 2) Also in column "Medical Examination Result" system should be demanding the input in MM/DD/YYYY format & not as MM/DD/YYYY Time. | Promact to check and confirm
Module - Compliance Management |  |  |  | Export to Excel, Bulk upload, & download Excel functionality should be operative | As of now hold